## Sheet1
Project Implementation Tracker
Problem Statement
Outcome Proposed
S.No. | Date | Time Invested(in mins) | Work Details | Place Description | Stakeholders | Challenge Faced | Outcome of the day
1 | 2023-04-01 | 1 hr 15 mins | Online discussion | Google meet | Us | 1. Getting everyone ready come at the same time; 2. Internet Connectivity issue; 3. Not everyone speaking and taking things for granted | 1. Healthy discussion on how to complete the task
2 | 2023-04-03 | 2 hr 15 mins | Went there, gathered information | It is a place near ITO and the nearest bus stand is "Rainy well". It is a quite spreaded settlement of a small group of people belonging to different backgrounds. | Rainy well community | 1. NGO was hard to find; 2. People weren't open to the idea of discussing the problem; 3. At first it was hard to connect to children. | 1. Everyone was really happy because we got to connect with children and experiential learning is the best.
3 | 2023-04-04 | 1 hr | Nexy day, entry denied | Same as before, this time they were a little rude | Us | 1. NGO asked us to get permission from their head through site. Bureaucracy kicking in. | 1. Shattered
4 | 2023-04-05 | 30-45 mins | Contacted NGO through there online portal and number but nothing happened | NA | NGO | 1. Wrong number issue; 2. | 1. Disappointment
5 | 2023-04-23 | 30 mins | Regrouping what we can do | Online google meet | Us | 1. A lot of challenges were to be addressed. | 1. Pivoting on what the original idea was; 2. Facing challenges
6 | 2023-04-24 | 2hr 30 mins | Went there, spent time with kids | We went to the same location but this time we straight away approached the kids and their parents to counsel. We got a place near their houses, close to nature. | Rainy well community | 1. Was tough to directly connect with parents and kids. | 1. Overwhelmed by the happiness felt after directly connecting with small kids; 2. Fulfilled day
7 | 2023-04-25 | 1 hr 30 mins | Created presentation and compiled the work | NA | You | 1. Distributing work; 2. Regrouping the entire work done; 3. Technical issues | 1. Project complete